## Project Timeline
Date | Category | Event/Note | Attendee
2024-05-08 | Planning | PP SWC Cawn Issue
2024-05-11 | Finance | Solar Scope for Robbin ($553000)
2024-05-15 | Doc | Documentation
2024-05-31 | Planning | Angel AA Glovate Lavern Siki
2024-06-01 | Deadline | Submission Due
2024-06-04 | Planning | ILSA App NOFO FG Budget template Solar Sovereignty
2024-12-11 | Meeting | DDK in He
2024-12-13 | Meeting | Meeting
2024-12-14 | Meeting | EDDK with Goldie (Workforce)
2024-12-15 | Finance | Finalize Budget template
2025-04-08 | Operations | Walkthrough
2025-04-23 | Finance | Sub-removal prices
2025-04-28 | Task | Mike Challahan Action Item (Weatherization walkthrough)
2025-05-05 | Admin | GATA Checklist
2025-05-08 | Comm | Email from Brad (Walkthrough)
2025-05-09 | Comm | Email from Richard (BB Lavern)
2025-05-10 | Meeting | Zoom Meeting
2025-05-12 | Finance | Revision of Budget Template (Phase 1+2)
2025-05-22 | Finance | Pictures sent to Preston (Budget)
2025-06-28 | Scope | Revise Construction Scope
2025-06-29 | Scope | Behire Scope of Work
2025-06-30 | Planning | Lavern - RFP Construction Engagement
2025-08-11 | Comm | Email Behire for Intrat Scope
2025-08-25 | Meeting | Behire Meeting (Team discussing scope)
2025-08-29 | Meeting | Behire Meeting (BT Lavern Simply PP)
2025-09-08 | Assessment | Robbin Act Engineering Needs Assessment
2025-09-17 | Comm | Sent note (email) section of Design
2025-09-18 | Call | Richard & Brad (Spreadsheet of permit equipment and dumpsters)
2025-11-13 | Finance | $15000 allocation for Behire Intrat service
2025-11-14 | Admin | Victoria added Natural E
2025-12-17 | Docs | MOUs
2025-12-20 | Docs | SIFSH / Letter of Support / BT Eond PP Simply
2025-12-21 | Meeting | IFSA Meeting
2025-12-30 | Deadline | Application Ready
2025-12-31 | Admin | PP Grant Checklist
2026-02-09 | Meeting | Lavern Meeting with Doc Ruckers (Teams)
2026-02-17 | Finance | Construction cost for Robbins Doc Ruckers
2026-02-19 | Ops | Brad set walkthrough for Doc Rockers
2026-03-03 | Finance | Doc Rucker Construction cost
2026-04-02 | Performance | Victoria meet expectation of scope
2026-04-03 | Performance | Lavern meet for expectation of scope
2026-04-14 | Comm | Lavern email about Artifact services / PFR and scopes
2026-04-15 | Finance | Payout schedule
2026-04-17 | Comm | Lavern email contractor list
2026-04-19 | Finance | PFR and second distribution payout