## Construction budget
Contractors | ROM
Roofers | 148500
Mechanical - HVAC | 180000
Electrician | 250000
Floor installers | 180000
Carpenters | 95000
Insulator | 40500
Plumbers | 50000
Bricklayers | 135000
Painter | 80000
Laborers | 45000
Total without CON | 1204000
Contingency 10% | 120400
Total with CON | 1324400
Insulator cost estimate breaks down into two parts.
1) $27,000 for sealing & testing
2) $13,500 for instulation & Wrapping work
10 % Contingency added for overall project

## Roofer scope
Roofer scope
Demo exisitng layers and deteriorating support
Replacing and repairing any sturcutral support
Installing energy efficient reflective layers (white)
Replacing or repairing damaged sturcutral layers
Installing new gutters
Flash the HVAC unit roof curbs / prep
Flash the Exhaust flue piping
Water Roof Testing (leak check)

## Mechanical - HVAC scope
Mechanical - HVAC Scope
Install roof curbs for units
Minor gas piping to unit
Piping Gas line to Mechanics
installing BAS /energy efficient control measure
minor low voltage control to unit
Ductwork changes* (office,gym, washroom and etc)
inspect / Survey diffusers *(office,gym, washroom and etc)
inspect split HVAC units and pumps replace as needed
Commissioning the HVAC units Air balancing
Operational startup - heat exchanger burn in | * means investigate
Inspecting washroom exhaust fan - ductwork-Mechanical
inspecting Kitchen exhaust system - ductwork-Mechanical

## Electrician scope
Electrician Scope
Conduit and wires to HVAC equipment | Power
Conduit and wires to HVAC equipment | low voltage
Electrical distribution survey *
Distribution & panel upgrade
Lighting upgrade-(office,outside, gym,washroom, etc)
adding lighting control measure -(dimmers, occupancy sensors, etc)
installing heat trace for exsposed roof water lines and exposed piping
installing heat trace to prevent ice damming
Inspecting washroom exhaust fan - electrical
inspecting Kitchen exhaust system - electrical
upgrade egress ligting, signages and directions markers
appliances power survey *
commissioning and labeling appropriate power feeds
inspect / Survey smoke detectos and CO2 sensor*
replacing washroom elctrical hand dryers |  | * means investigate

## Floor installers Scope
Floor installers
installing wood floor for Gym
replacing /repair tile in damaged areas (ofice, hallways,washroom, etc)
replacing /repair carpet in damaged areas (ofice, hallways,washroom, etc)
Adding vinyl baseboard in appropriate areas
Adding vinyl quarter rounds in appropriate areas

## Carpenters Scope
Carpenters
Windows work
Installing Double pane energy efficient windows
Sealing window and framing
support /repair framing structure members and window pane
installing/replacing blinds , Window treament film for lessen solar load
Doors work
installing energy efficient and fire rate door
installing appropriate door hardware (kick plates, handles,sweeps and etc)
Support /repairing framing structure members
Ceiling
Patch, replace and repair damaged ceiling area (Tiles,Sheet rock, etc)
| inspect / survey ceiling grids in office ,hallways and exposed areas* | * means investigate
Misc
Repair exterior chainlink gate / fence
inspecting ktichen cabinetry
Repalcing soap dispenser in washroom and kitchen
Replacing Washroom and Kitchen towel dispensers

## insulator Scope
Insulator
Air seal
Air seal testing
Blow door test
Testing insulation for absetos *
insulation
Seal cracks, holes any open area inside and outside building
wrapping and insulating all expose piping inside /outside building
Labeling /identifier for insulated piping
Remove/replace/repair any damage insulation
* means investigate

## Plumber Scope
Plumber
Replace or repair Kitchen sinks
Replace or repair urines, toilets and sinks
Replace or repair bathroom stall partitions
Replace or repair Bathrooom and Kitchen water feeds (Hot &Cold)
Replace or repair Bathrooom and Kitchen drain line
install new hot water heaters and pump
upgrade drinking fountains to energy efficient models
Inspection trench drains around outside of building fro proper drainage *
pipe water line to the roof for future HVAC maintenances.
Piping Gas line to Mechanics
* means investigate

## Bricklayer Scope
Bricklayer
Façade repairs - Tuckpointing
Sealing bricks
Replacing or repairing parapet walls
Replace or repair claytile on roof edges and seal
Seal /repair any interior cinder blocks
Inspect building lentils *
* means investigate

## Painter Scope
Painter
Painting all areas and caulking after remodel
Testing for lead in building exiting surfaces *
Repairing or patching existing damage surfaces
Sealing moisture coating in areas expose to temperature varations | * means investigate
Caulking waterproofing - washroom and kitchen

## Laborer
Laborers
Consistency Clean up throughout the project
Site preparation
Material handling
Assisting Trade persons
Physical labors - dumpster
Demolition
Trash

## Phases for workflow
Work flow Sub-phasing
Phase One
1 | Roofers
2 | Electrician
3 | Plumbers
4 | Carpenters
5 | Bricklayer
6 | Labors
Phase Two
1 | Mechanical -HVAC
2 | Electrician
3 | Plumbers
4 | Carpenters
5 | Bricklayer
6 | Flooring
7 | insulators
8 | Labors
Phase Three
1 | Flooring
2 | Painting
3 | Bricklayer
4 | Plumbers
5 | insulator
6 | Electrician
7 | Carpenters
8 | Labors
Phase Four - Final finishing & commissioning /Testing
1 | Mechanical -HVAC
2 | Painting
3 | Carpenters
4 | Plumbers
5 | insulator
6 | Electrician
7 | labors